## Slide 1
Overall Program Summary
As of Dec : 15-19
Resources | Timeline | RAID | Overall Program Status
G | A | A | A
Overall Statement
Key Accomplishment for the period:
• Hybrid engine implemented (real-time data + simulated execution) • Safety balance checks validated • Email alert system fixed (SMTP SSL – Port 465) • End-to-end trade lifecycle tested successfully
Planned Activities next period:
• Configure production API keys • Execute real-money pilot trade • Finalize deployment and startup scripts
# | Milestone | RAG / Due Date
1 | Environment Setup | 11/15
2 | DB & Auth Integration | 11/20
3 | Sprint 0 – API Integrations | 11/25
4 | Sprint#1,2,3 - Trading Engine | 12/05
5 | Sprint #4,5,6 – Email Alerts | 12/08
6 | Sprint #7,8,9 – Prod Hardening | 12/19
7 | Pilot Trade | 12/30
8 | Optimization | 2/29
On track
At Risk
Off Track
Completed
Not Started /On Hold
No Baseline
Reason for Amber: 1. External dependency – Production Go-Live pending Real Trading API Keys from Project Manager.
The SmartTrade Algo Trading system has completed critical development and hybrid architecture phases. The system is fully operational in simulation mode using real-time market data from Binance. All core modules are integrated and tested.